## Gantt Chart IIP
https://goo.gl/PlIwL0
PROJECT TITLE | SENSE |  |  |  |  | AUTHOR | [8 empty] | SENSE Team
PROJECT MANAGER | René García |  |  |  |  | DATE | [8 empty] | 16/04/2026
[6 empty] | 2026-03-21 |  |  |  |  | 2026-03-28 |  |  |  |  | 2026-04-04 |  |  |  |  | 2026-04-11 |  |  |  |  | 2026-04-18 |  |  |  |  | 2026-04-25 |  |  |  |  | 2026-05-02 |  |  |  |  | 2026-05-09 |  |  |  |  | 2026-05-16
[6 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE
TASK TITLE | TASK OWNER | START DATE | DURATION | DUE DATE | % OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9
[6 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Review all the report and define objectives, constraints, risks and limitations. | Everyone | 2026-03-21 | 7 | 2026-03-28 | 100% | bar: WEEK 1 M to WEEK 1 F
Create a deck of slides for the progress done on Week 1 | Everyone | 2026-03-14 | 7 | 2026-03-21 | 100% | bar: WEEK 1 M to WEEK 1 F
Set-up PLECS licences | Cami | 2026-03-21 | 13 | 2026-04-03 | 100% | bar: WEEK 2 M to WEEK 3 R
Ensure NDA signed by everyone and the full access to the previous project | René | 2026-03-22 | 13 | 2026-04-04 | 75% | bar: WEEK 2 M to WEEK 3 R
Run a complete test and document it | Cami | 2026-03-23 | 13 | 2026-04-05 | 0% | bar: WEEK 3 M to WEEK 3 F
Document the status of software modules; identify improvement points | René | 2026-04-06 | 14 | 2026-04-20 | 0% | bar: WEEK 3 M to WEEK 4 F
Visit KTH Double-pulse testing facilities and create report | Jeremy | 2026-04-07 | 7 | 2026-04-14 | 100% | bar: WEEK 3 M to WEEK 3 F
Research and review automotive standards for power converters | René | 2026-04-08 |  | 2026-04-08 | 100% | bar: WEEK 3 M to WEEK 3 F
Optimize sensitivity tests | René | 2026-04-16 | 14 | 2026-04-30 | 0% | bar: WEEK 4 T to WEEK 5 F
Define clear objectives on which libraries and how to use them | Vaishnavi | 2026-04-17 | 7 | 2026-04-24 | 0% | bar: WEEK 4 T to WEEK 4 F
|  |  | 0 | 0 | 0%
0
|  |  | 0 | 0 | 0%
|  |  | 0 | 0 | 0%
|  |  | 0 | 0 | 0%
|  |  | 0 | 0 | 0%
|  |  | 0 | 0 | 0%
|  |  | 0 | 0 | 0%
0
|  |  | 0 | 0 | 0%
|  |  | 0 | 0 | 0%
|  |  | 0 | 0 | 0%
|  |  | 0 | 0 | 0%
Formulas:
DUE DATE = [START DATE]+[DURATION]